**August - Purple**

**September- Red**

**October - Green**

**November- BLUE
December - Orange**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **School Keys Strands and AdvancEd Standards** | **Actions, Strategies, and Interventions** | **Timeline** | **Estimated Costs, Funding Sources, and Resources** | **Person(s) Responsible** | **Evaluation of Implementation of Strategies and Impact on Student Learning** |
| **Action Steps Toward Implementation** |
| *Competency/Rigor* | 70% percent of ALC students will be on pace to achieve 50% progress or more in 4 core subject courses. |
| AdvancEd standards 3.11 | * Implement Content PLC’s
	+ Planning Period 4 Cornerstone
	+ Edcamp during Professional Learning
 | August-May | None | GrayRich | * Began PLC lesson plans discussing future PLC dates and expectations
* Organize teachers to film their lessons for PLC observations.
 |
| AdvancEd standards3.25.1 | * Implement a 1 on 1 tutoring program for students with the lowest achievement
 | August-May | None | ThreadgillGrayRich | * Sent in approval for the county.
* Begin tutoring starting 9/6 and will continue tutoring Monday - Thursdays after school.
 |
| AdvancEd standards  | * Create Progress Boards (Main Hallway /Teacher Classrooms)
 | August-May | -Board Cost | ThreadgillGrayRich | * Boards created and discussed in classes.
* Began placing students who completed courses outside on board to promote success
 |
| AdvancEd standards  | * Student Progress Monitoring
 | August - May | N/A | GrayRich | * Created google document for teachers to update students weekly progress
* Continue to mark progress in google doc and mentor students who need assistance.
 |
| *Character* | Within the first month of enrollment in the Alternative Learning Center, 100% of students will take part in a personal and career interest survey that will be used to develop a transition plan.  |
| AdvancEd standards  | * Real Time

  | August - May | N/A | Gray Rich | * Created real time Canvas pages
* Taught first real time lessons to teachers and students
* Teachers begin teaching PLC real time and using their lessons in the classroom.
 |
| AdvancEDstandards | * Implement Student Directed Career Meetings
	+ Induction
	+ Mid Year
 | August - May | N/A | GrayRich | * Passed out career inventory with all students
* Began meeting with students and discussing career goals and plans.
* Organize goals and plans with students weekly
 |
| *Character* | 100% of all ALC students during the 2018-19 school year will enrolled into a Real Time mentorship advisement to address students Social and Emotional learning needs as measured by the completion of strategies and activities. |
| AdvancEd standards  | * Canvas Based SEL Character Program
	+ Induction Meetings
 | August - May | N/A | GrayRich | * Perform in depth parent and student meetings regarding policies and procedures at ALC
* Continue with induction process and working with home schools to make process more effecient.
 |
| AdvancEdstandards | * Real Time Mentorship
	+ Positive Interactions (Greeting As walk in, Praising Positive Behaviors)
 | August - May | N/A | GrayRich | * Discussed standard for teachers with interactions
* Start every class and school with shaking hands and positive interactions
* Discuss ways to ensure we continue positive interactions and create new positive interactions
 |
| *Character* | **Develop a systematic plan to increase stakeholder involvement.** |
| AdvancEd standards3.12 | * Improve School Communication
	+ Create School Website
	+ Implement Good News Cards
	+ Improve Communication with parents through discipline process.
 | August-May | N/A | GrayRich | * Created a school website for all community to use
* Created Good News Cards for teachers to send home
* Began calling home with all students good and bad
* Call home after all student behavior problems.
* School website updated weekly with new information
* Teachers have been calling home for good news.
 |